## Projects
Generator Interconnection Status Report | August 2017
Date: 9/1/2017 3:45:12 PM

## Newly Operational & Cancelled
New Resources Approved for Synchronization
INR | Project | MW | County | Part2 Synch Apprv
15INR0070_1b | SIRIUS_UNIT2 (Pearl Solar) | 50 | Pecos | 2017-08-24
16INR0065b | SPTX12B (CED Upton Solar) | 157.5 | Upton | 2017-06-30
New Resources Approved for Commercial Operation
INR | Project | MW | County | Resource Commissioning Date*
16INR0122 | Blue Summit Battery | 30 | Wilbarger | 2017-08-11
16INR0065b | SPTX12B (CED Upton Solar) | 157.5 | Upton | 2017-08-25
*Defined in Section 2 of the ERCOT Nodal Protocols: The date on which ERCOT declares that a Resource has completed all qualification testing administered by ERCOT as part of the Resource Interconnection process so that a Resource is approved for participation in ERCOT market operations.
Projects Cancelled by the Developer*
INR | Project | MW | County | Cancellation Date
19INR0024 | Lacy Creek W | 400 | Glasscock | 2017-08-31
13INR0006 | Grandview (Last) W | 750 | Gray | 2017-09-01
*Includes only those projects cancelled after developer makes a Full Interconnection Study request.

## Full Study Table
All Projects, in the Full Interconnect Study (FIS) phase, without a Signed Interconnection Agreement as of August 31, 2017
GINR Reference Number | Project Name* | Point of Interconnection (POI) | County | Fuel | Capacity to Grid (MW) | Projected Month/Year (as specified by the resource developer) | Status
12INR0055 | Little Mountain Wind | tap 69kV radial LakeKempSw 782 - LakeKemp 783 | Baylor | WIND | 80 | 6/2018 | Incomplete
13INR0025 | Buffalo Wind 1 | 79504 AJ Swope 345kV | Randall | WIND | 150 | 7/2018 | Complete
13INR0006 | Grandview (Last) W | 79000 Gray 345kV | Gray | WIND | 750 | 12/2018 | Incomplete
* The capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or negative values.

## IA Table
Generation Interconnection Agreements as of August 31, 2017
Planning Guide Section 6.9 Requirements
(Other than model data submission)
GINR Reference Number | Project Name | Interconnecting Entity | County | Projected Date | Fuel | MW For Grid | Changes From Last Report | Meets Section 6.9 Requirements (1)(b) through (1)(d) | Sufficient Financial Security Received by TSP | Air Permit(s) | Proof of Adequate Water Supplies | FIS completion
15INR0070_1b | SIRIUS_UNIT2 (Pearl Solar) | OCI Solar | Pecos | 9/2017 | Solar | 50 | Project Name, Projected Date | Yes | Yes | N/A | N/A | Complete
13INR0049 | FEGC (Friendswood) | Friendswood Energy Genco | Harris | 9/2017 | Gas | 129 | Project Name | Yes | Yes | Yes | Yes | Complete
14INR0027 | Guadalupe II | Calpine | Guadalupe | 6/2019 | Gas | 362 |  | No | Yes | Yes | No | Complete

## Wind Chart
INR | ProjectName | County | Status | Projected Date | IA Signed | Fuel | TypeCode | MWForGrid | Year | FS Posted
11INR0082a | FERMI (Val Verde Wind ) | Val Verde | PLANNED | 2017-09-15 | 2015-08-12 | WIND | WT | 149 | 2017 | true
16INR0055 | SANTACRU (Chapman Ranch Wind I) | Nueces | PLANNED | 2017-09-18 | 2015-07-16 | WIND | WT | 250 | 2017 | true

## Solar Chart
INR | ProjectName | County | Status | Projected Date | IA Signed | Fuel | TypeCode | MWForGrid | Year | FS Posted
15INR0070_1b | SIRIUS_UNIT2 (Pearl Solar) | Pecos | PLANNED | 2017-09-15 | 2014-12-17 | SOLAR | PV | 50 | 2017 | true