## Summary
Summary |  |  | Major GIM Milestone Status by Fuel/Technology Type, MW
Currently tracking 1890 generation interconnection or change requests as of Aug 31, 2026 |  |  | Includes only those (1) Large Generator projects for which a Screening Study has been requested, (2) Small Generators for which an interconnection request has been made, and (3) projects that are not Inactive
GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER STUDY |  |  | Fuel | Technology | SS Started | SS Started | SS Completed | SS Completed | SS Completed | SS Started | SS Started | SS Completed | SS Completed | SS Completed | Small Generator | Small Generator | TOTAL
Includes only those (1) Large Generator projects for which a Screening Study has been requested, |  |  | Type | Type | FIS Not Started | FIS Started | FIS Not Started | FIS Started | FIS Completed | FIS Not Started | FIS Started | FIS Not Started | FIS Started | FIS Completed | Not Model Ready | Model Ready
(2) Small Generators for which an interconnection request has been made and |  |  |  |  | No IA | No IA | No IA | No IA | No IA | IA | IA | IA | IA | IA
and (3) projects that are not Inactive
Status of SS, FIS and IA | Project Count | % of Total | Gas | Combined-Cycle |  | 4543.9 | 4708 | 28913.39 | 34.5 |  |  |  | 6390.5 | 1371 | 9.9 | 9.3 | 45980.49
LARGE GENERATORS |  |  | Gas | Combustion Turbine | 173 | 3022.58 | 18 | 11018.14 | 736.5 |  |  |  | 4058.71 | 3347.46 |  |  | 22374.39
SS Started, FIS Not Started, No IA | 4 | 0.0021164 | Gas | Internal Combustion Engine |  | 3331.58 |  | 6912.33 |  |  |  |  | 800.91 | 925.38 | 9.99 | 19.89 | 12000.08
SS Started, FIS Started, No IA | 44 | 0.02328 | Gas | Compressed Air Energy Storage
SS Completed, FIS Not Started, No IA | 41 | 0.021693 | Gas | Steam Turbine |  |  |  | 1335 | [5 empty] | 14 |  |  | 1349
SS Completed, FIS Started, No IA | 1048 | 0.5545 | Gas | Fuel Cell
SS Completed, FIS Completed, No IA | 106 | 0.056085 | Gas | Total gas | 173 | 10898.06 | 4726 | 48178.86 | 771 |  |  |  | 11250.12 | 5657.84 | 19.89 | 29.19 | 81703.96
SS Started, FIS Not Started, IA | 0 | 0 | Coal
SS Started, FIS Started, IA | 0 | 0 | Wind |  |  | 1708.91 |  | 26956.92 | 287.02 |  |  | 486.4 | 10426.07 | 8265.44 |  |  | 48130.76
SS Completed, FIS Not Started, IA | 5 | 0.0026455 | Solar |  | 450 | 3740.94 | 5496.87 | 78433.95 | 4798.43 |  |  | 304.94 | 35098.2 | 27917.41 | 30.68 | 17.95 | 156289.37
SS Completed, FIS Started, IA | 272 | 0.14392 | Biomass
SS Completed, FIS Completed, IA | 303 | 0.16032 | Other | Battery | 401 | 1791 | 3709 | 109613.85 | 10900 |  |  | 133 | 17039 | 20343 | 273 | 213.1 | 164416.95
SMALL GENERATORS |  |  | Other* |  |  |  | 930 | 2980.15 | [7 empty] | 19.9 | 3930.05
Not Model Ready* | 35 | 0.018519 | TOTAL |  | 1024.11 | 18138.57 | 14862.14 | 266164.16 | 16756.43 |  |  | 924.32 | 73813.63 | 62183.89 | 323.25 | 280.62 | 454471.12
Model Ready* | 32 | 0.016931 | * Other includes petroleum coke (pet coke), hydroelectric, nuclear, fuel oil, geothermal energy, other miscellaneous fuels reported by developers, and fuel cells that use fuels other than natural gas.
Total Interconnection Requests | 1890
Inactive (since last month) | 10
Cancelled (since last month) | 19
Capacity, MW
Total Capacity Under Study | 454471.12
Interconnection Agreements Executed | 138386.94
Inactive (since last month) | 2085.14
Inactive changed to Planned (since last month) | 1430.72
Inactive changed to Cancelled (since last month) | 0
Cancelled (since last month) | 4581.34
* "Not Model Ready" means that a Small Generator's data has not yet been loaded into the Network
Operations Model. "Model Ready" means that the data has been loaded into the NOM, and the Resource is
ready to begin the commissioning process.

## Project Details - Large Gen
GIM Project Details - Large Generators
NOTES:
Due to Protocol confidentiality provisions, only those projects for which a Full Interconnection Study has been requested are included.
Excludes projects that have a status of Inactive (status = INA).
The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or
negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.
The construction start date is the date physical on-site work of a significant nature (such as excavation for footings or foundations or pouring of concrete for foundations)
has begun and is on-going. Additionally, major equipment items (such as turbines or step-up transformers) are on-site, in route to the site, or being manufactured under a
binding contract with significant financial commitments. The construction end date is the date when all plant systems are ready for commissioning/startup activities. Note
that the reporting of Construction Start and End Dates will not begin until ERCOT's online GIM system is available to project developers for data entry.
Blank cells on Air Permit, GHG Permit and Water Availability indicate the emission permits/proof of water supplies are required but have not been obtained or reported to ERCOT yet.
A developer may split a project into two or more additional projects with different INR numbers during the interconnection request process. Due to current RIOO interface limitations,
the new projects do not inherit certain milestone dates entered for the original project. As a result, dates may be blank even though the milestones have been met.
A “1-1-1900” date is used to signify that an actual date for a project milestone is not available. This typically occurs for project data migrated from the legacy GINR database to the RIOO system.
Project Attributes | [10 empty] | Changes from Last Report | GIM Project Milestone Dates
INR | Project Name | GIM Study Phase | Interconnecting Entity | POI Location | County | CDR Reporting Zone | Projected COD | Fuel | Technology | Capacity (MW) |  |  | Screening Study Started | Screening Study Complete | FIS Requested | FIS Approved | Economic Study Required | IA Signed |  | Air Permit | GHG Permit | Water Availability | Meets Planning | Meets All Planning |  | Construction Start | Construction End | Approved for Energization | Approved for Synchronization | Comment
[11 empty] | Change indicators: Proj Name, MW | Approval Date for | [6 empty] | Financial Security |  |  |  | Guide Section 6.9(1) | Guide Section 6.9 | Meets Planning Guide
[11 empty] | Size, COD, SFS/NtP, FIS Request, | Submission of Proof of | [6 empty] | and Notice to |  |  |  | Requirements for | Requirements for | QSA (Section 5.9)
[11 empty] | Status Change INA-to-PLN | Site Control | [6 empty] | Proceed Provided |  |  |  | Inclusion in Planning | Inclusion in Planning | Prerequisites
[23 empty] | Models | Models
15INR0064b | Harald (BearKat Wind B) | SS Completed, FIS Completed, IA | McCrae Wind Energy II, LLC | 59903 Bearkat 345kV | Glasscock | WEST | 2026-12-03 | WIN | WT | 162.1 |  |  | 2013-11-27 | 2014-01-27 | 2014-04-15 | 2017-09-27 | No | 2018-05-30 | Yes | Not Required | Not Required | Not Required | 2018-05-30 | 2018-09-19 | 2019-01-22 |  |  | 2020-02-10 | 2020-05-12
16INR0049 | Nazareth Solar | SS Completed, FIS Completed, IA | TX Nazareth Solar, LLC | tap 345kV 23914 Tule Canyon - 23912 Ogallala C2 | Castro | PANHANDLE | 2027-08-31 | SOL | PV | 203 |  | 2014-07-07 | 2014-06-19 | 2014-07-25 | 2014-07-01 | 2025-07-29 | No | 2026-03-05 | Yes | Not Required | Not Required | Not Required | 2024-03-22
22INR0467 | Bird Dog Energy Storage | SS Completed, FIS Completed, IA | VESI 37 LLC | 5669 Argenta 69kV | Live Oak | SOUTH | 2026-10-23 | OTH | BA | 60.4 | COD | 2022-06-02 | 2021-02-04 | 2021-04-19 | 2022-05-19 | 2025-06-18 |  | 2024-02-16 | Yes | Not Required | Not Required |  | 2024-02-16 | 2025-08-07 | 2025-09-22 |  |  | 2026-08-05 | 2026-08-28
23INR0249 | Limewood Solar | SS Completed, FIS Completed, IA | Limewood Bell Renewables, LLC | 3420 Temple Pecan Creek 138kV | Bell | NORTH | 2026-12-29 | SOL | PV | 204.6 |  | 2021-11-03 | 2021-04-30 | 2021-07-22 | 2021-10-06 | 2025-03-14 | No | 2023-02-22 | Yes | Not Required | Not Required | Not Required | 2025-02-13 | 2025-05-01 | 2025-05-01 |  |  | 2026-08-10

## Project Details - Small Gen
GIM Project Details - Small Generators
NOTES:
Due to Protocol confidentiality provisions, only those Small Generator projects are included for which ERCOT has (1) received written Notice from Interconnecting Entities (IE) that authorize the project
information to be made public, or (2) approved the IE's completed Resource Registration form as indicated by assignment of a “Model Ready Date".
Excludes projects that have a status of Inactive (status = INA).
INR | Project Name | Model Ready Date | Interconnecting Entity | POI Location | County | CDR Reporting Zone | Projected COD | Fuel | Technology | Capacity (MW) | Change indicators: Proj Name, MW | IA Signed | Financial Security | Approved for Energization | Approved for Synchronization | Comment
[11 empty] | Size, COD, SFS. |  | Required to fund
[11 empty] | Status Change INA-to-PLN |  | Dist. Upgrades
22INR0596 | Grizzly Ridge BESS SLF | 2022-09-01 | Grizzly Ridge Solar LLC | Pottsville Switching Substation (Bus# 178) | Hamilton | NORTH | 2030-07-01 | OTH | BA | 0 |  | 2021-10-18 | Yes | 2023-02-10
26INR0574 | Apple BESS | 2025-12-10 | Apple Infra LLC | Station Name - Apple Oncor 5-digit code - APPLE Oncor XFMR # - 1 ERCOT Bus Name - APPLE_9 ERCOT Bus # 1276 EROCT Load Name - LDLXFMR1 Substation Transmission kV - 138 | Ector | WEST | 2026-10-05 | OTH | BA | 9.9 |  | 2025-04-03 | Yes | 2026-08-04

## Commissioning Update
Commissioning Approvals during August 2026
Commissioning Category | INR | Size Category | Project Name | Fuel | County | Approval Date * | MW **
Commercial Operation Approved by ERCOT* | 24INR0294 | Large | Citrus Flatts BESS | Battery Storage | Cameron | 2026-08-07 | 103.01
Synchronization Approved by ERCOT | 22INR0467 | Large | Bird Dog Energy Storage | Battery Storage | Live Oak | 2026-08-28 | 60.4
Energization Approved by ERCOT | 22INR0467 | Large | Bird Dog Energy Storage | Battery Storage | Live Oak | 2026-08-05 | 60.4
Energization Approved by ERCOT | 26INR0574 | Small | Apple BESS | Battery Storage | Ector | 2026-08-04 | 9.9
Energization Approved by ERCOT | 23INR0249 | Large | Limewood Solar | Solar | Bell | 2026-08-10 | 204.6
* For projects approved for commercial operations, the approval date is the Resource Commissioning Date defined in Section 2 of the ERCOT Nodal Protocols: The date on which ERCOT declares that a
Resource has completed all qualification testing administered by ERCOT as part of the Resource Interconnection process so that a Resource is approved for participation in ERCOT market operations.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or negative
values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.

## Inactive Projects
Inactive Projects as of end of August 2026*
INR | Size Category | Project Name | Fuel | County | Inactive Date | MW **
13INR0010a | Large | Mariah Del Este Wind | Wind | Parmer | 2019-09-09 10:19 | 152.5
17INR0022 | Large | MIRAGE | Gas | Harris | 2023-05-31 11:28 | 11
* Includes only those projects designated as Inactive by ERCOT or the project developer after the developer makes a Full Interconnection Study (FIS) request, or
in the case of Small Generators, after their Resource Registrations have been approved.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may
have zero or negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW
available to the grid.

## Cancellation Update
Projects Cancelled by the Developer during August 2026*
INR | Size Category | Project Name | Fuel | County | Cancel Date | MW **
21INR0280 | Large | Edgewater Storage | Battery Storage | Ellis | 2026-08-11 14:29 | 50
22INR0337 | Large | Skylab Solar | Solar | Wharton | 2026-08-13 12:19 | 609.74
* Includes only those projects cancelled by the developer after it makes a Full Interconnection Study (FIS) request, or in the case of Small Generators, after the Resource Registrations have been approved.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may
have zero or negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW
available to the grid.